## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Alison Bennett MP has asked for sight of relevant correspondence
Flashing School warning lights to be considered
School Parking | 2023-04-01 | JD/IM | School considering staggered drop off/pick up times
Conversion of grassed area outside school not supported by Councillors
PC to consider additional warning signs
Sayers Village Proposals | Dec | JS | Meetings with Sayers Village Society Twineham, Hurst PC and WILD 8th Dec & 19th Jan
Sayers Village Liaison Group Mtg 14 Jan and 23rd Jan
Meeting with Wates 8th Jan and Reside tba
Speedwatch Scheme | 2025-11-01 | IS
Watershed actions to be determined | 2023-01-01 | IM/SA | Riperian Owners Kits available . To be printed and sent to landowners
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known.
Re-Wilding | 2025-11-01 | IS | Post to be removed. Bulbs planted in MG. Plug wildflower plants to be planted in Spring
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba.
APC Website Update | 2024-06-01 | IM | Vision ICT recommendations to be considered and developed by Iain.
B2118 pathway towards Muddleswood | 2024-07-01 | JP | MSDC to clear pathway overgrowth/siding work. Tim Boxall contacting owners.
Allotments Water Supply | 2024-09-01 | SS/SA | Water Butt to be repainted (Spring). Guttering needs repair by Clarion
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance of leaves etc reported to MSDC Street Cleaning. Gully cleared but filling again.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Joy Dennis advises that Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - east side | 2025-02-01 | IS/IM | GW Shelter installed. Section 106 funds?
WSCC Bus Services Improvement Fund may also provide finance. Joy D to advise
Copper in a Café | 2025-02-01 | ? | Arrange?
Allotment Rubbish | 2025-03-01 | JP/IM/SA | AD Rowe to clear in Spring 26. "No Dumping" sign required.
Street Road Signs | 2025-09-01 | SS | MSDC refuse to replace faded signs. PC to arrange. Brethren Church ?
Trees | 2025-09-01 | SS /IM | Park Linden to be trimmed.
Dropped gully by school | 2025-11-01 | ? | Repaired but starting to drop again. Report to WSCC Highways.
Under 5s Rate | 2025-11-01 | JD/JS/DS | Revised rate determined and contract drafted. To be presented to Under 5s Group.
IM
SID Data | 2026-01-01 | JD | Required for Sayers Village Proposals. Dave Robson has offered to undertake.