## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Further Action to be decided
Re-routing of School Bus | 2023-04-01 | JD/IM | Germma Wallis to investigate options with WSCC School Transport Scheme staff
School to be encouraged to produce an Active Travel Plan
Clean and Repaint Village Gateways | Oct | JD/JP | Gateways cleaned. Veg needs clearin. De-rusting and painting of bolts tba.
Sayers Village Proposals | Nov | JS | Second Engagement Meeting with MSDC Planning tba
Meeting with Neighbouring PCs on 8th July
Speedwatch Scheme | 2023-01-01 | IS | Truslers Hill Lane to be Scheduled. Six speeders recorded on B2118 (N&S)
Watershed actions to be determined | 2023-01-01 | SA | Riperian Owners Kits available?
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help and timing to be determined
Re-Wilding | 2024-02-01 | SS/JP/SA | Wildflower seeds to be planted Spring 2025. Grass cutting by SA after daffodils.
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba
APC Website | 2024-06-01 | IM | To be updated. Vision ICT to recommend improvements
Strimmer Purchase | 2024-07-01 | JP/IM | Choice to be reviewed with Brian Spring 2025. Need for Insurance? Storage?
The Street/Barleycroft hedge | 2024-09-01 | IM | Trimming to be deferred until end of nesting season
B2118 pathway | 2024-07-01 | JP | Pavement needs attention. MSDC to clear overgrowth/WSCC to do Siding if needed
Allotments Water Supply | 2024-09-01 | SS | Installing waterpipe too expensive. Water Butt to be provided
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance reported to MSDC Street Cleaning Team. WSCC to clear Gully
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - east side | 2025-02-01 | IS | Consider new build and Installation. Land ownership is WSCC
WSCC Bus Services Improvement Fund may provide finance. Joy D to advise
Copper in a Café | 2025-02-01 | ? | Arrange?
Dog Bin | 2025-03-01 | IM/SA | For disposal
Allotment Rubbish | 2025-03-01 | JP/IM/SA | Clarion to provide quotation for clearing. "No Dumping" sign required.
Silent Soldiers | 2025-04-01 | JD/JP/DR | Move out of MG for Victory over Japan day?
Millenium Garden + Pound | 2025-04-01 | JP | Pound clearance unsatisfactory
Broken Bench | 2025-06-01 | JP/IM | MSDC/Glendale to replace?
Hedge Damage | 2025-06-01 | JP | Between Barn Close property and VH car park
Annual Grit Bin Audit | 2025-06-01 | IM/SA | Bins to be checked for repairs and grit