## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Rejection of 20 mph TRO in the context of other TRO decisions and 300 signature petition
to be raised with newly appointed WSCC Highways Councillor
Alison Bennett MP has asked for sight of relevant correspondence
Flashing School warning lights to be considered
Issue to feature as input to Sayers Village/Draft Plan
School Parking | 2023-04-01 | JD/IM
Restricted parking in Barn Close to be considered
PC to consider additional warning signs
Sayers Village Proposals | Feb | JS | Inspectors review of Draft Plan awaited.
Loops base case data available
Speedwatch Scheme | 2025-11-01 | IS | 5 Speeders caught on B2116 during 1 hour March session
Watershed actions to be determined | 2023-01-01 | IM | Riperian Owners Kits available . To be printed and sent to landowners
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known?
Re-Wilding | 2025-11-01 | IS | Post to be removed.
Flanders poppy seeds and more plugs to be planted (October)
Drainage meeting with S White (Sayers Common) | 2024-04-01 | JS/JD | Action Notes to be circulated. Next mtg tba.
APC Website Update | 2024-06-01 | IM | Vision ICT recommendations to be considered and developed by Iain.
B2116 Lay By and Gully | 2024-11-01 | IM | Clearance of leaves etc reported to MSDC Street Cleaning. Gully cleared but filling again.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
Copper in a Café | 2025-02-01 | ? | Arrange?
Allotment Rubbish and Vacant lots | 2025-03-01 | IM | AD Rowe to clear in Spring 26. "No Dumping" sign required.
Dropped gully by school | 2025-11-01 | ? | Repaired but starting to drop again. Reported to WSCC Highways.
Rec Area Bird Box | 2026-02-01 | SS/IM | fallen box collected by Glendale
SID data | 2026-01-01 | JD | Data being collected in connection with Sayers Village proposals
Extra SID??
Playground | 2026-02-01 | IM | Aditional "No Dogs Allowed" signs required. Glendale are dealing
The Street Mud/Blocked Gullies | 2026-02-01 | SS/IM | Blocked throughout village. Reported.
Twinham Lane Finger Post | 2026-01-01 | IM | New Post installed. Fingers to be installed
Footpath near Yew Tree Cottage | 2026-02-01 | SS/IM | Concrete post required to prevent traffic?. Ownership of land to be determined.
BasketballCourt | 2026-04-01 | SS/IM | Renovation needed by Glendale
End of Barn Close adoption | 2026-05-01 | SS | Potholes to be repaired
School Children Signs | 2026-05-01 | IS | To be moved to more prominent positions.
Rusted Albourne Road Sign | 2026-05-01 | IM | Reported to WSCC Highways
The Street Verges | 2026-05-01 | ? | Peter Holding?
Alboune Connected | 2026-05-01 | ? | Possibility of creating an APC page