## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO decision re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Despite petition TRO has once again been rejected by WSCC Highways
Meeting with Gemma Wallis | 2025-01-01 | JD | Meeting arranged for 9.30am 29th April to progress outstanding Highways issues
Re-routing of School Bus | 2023-04-01 | JD/IM | Germma Wallis to investigate options with WSCC School Transport Scheme staff
School to be encouraged to produce an Active Travel Plan
Clean and Repaint Village Gateways | Oct | JD/JP | Gateways cleaned and veg cleared. De-rusting and painting of bolts to be scheduled..
Sayers Village Proposals | Nov | JS | Engagement Meeting with MSDC Planning Dept arranged for 20th May
Speedwatch Scheme | 2023-01-01 | IS | B2116 residents needed to join team. Next event tba during better daylight
Watershed actions to be determined | 2023-01-01 | SA | Riperian Owners Kits to be provided
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help and timing to be determined
Re-Wilding | 2024-02-01 | SS/JP/SA | Wildflower seeds to be planted Spring 2025. Grass cutting by SA after daffodils.
Blocked and Dropped Drain by School Gate | 2024-04-01 | SA/SS | Tim Boxall has confirmed that repairing the The Street gully is a listed job
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba in March
APC Website | 2024-06-01 | IM | To be updated. Vision ICT to recommend improvements
Strimmer Purchase | 2024-07-01 | JP/IM | Choice to be reviewed with Brian Spring 2025. Need for Insurance?
The Street/Barleycroft hedge | 2024-09-01 | IM | Trimming to be deferred until end of nesting season
B2118 pathway | 2024-07-01 | JP | Pavement needs attention. MSDC to clear overgrowth/WSCC to do Siding if needed
Allotments Water Supply | 2024-09-01 | SS | Installing waterpipe too expensive. Water Butt to be provided
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance reported to MSDC Street Cleaning Team
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Braking Data may help when available
Church Lane - hedges overgrowing road | 2025-01-01 | JP | All hedges cleared except for Ragged Dog . Tim Boxall has contacted owner
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - west side | 2025-02-01 | IS | Brethren Church have refurbished
B2118 Bus Shelter - east side | 2025-02-01 | IS | Consider new build and Installation. Land ownership is WSCC
WSCC Bus Services Improvement Fund may provide finance
Copper in a Café | 2025-02-01 | ? | Arrange?
Dog Bin | 2025-03-01 | IM | For disposal
Allotment Rubbish | 2025-03-01 | JP | AD Rowe to clear
Silent Soldiers | 2025-04-01 | JD/JP/DR | Moved to The Street to mark VE day
Millenium Garden | 2025-04-01 | JP | Spring Clean. AD Rowe?