## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Alison Bennett MP has asked for sight of relevant correspondence
Flashing School warning lights to be considered
Issue to feature as input to Sayers Village/Draft Plan
School Parking | 2023-04-01 | JD/IM | School considering staggered drop off/pick up times
Conversion of grassed area outside school not supported by Councillors
PC to consider additional warning signs
Sayers Village Proposals | Feb | JS | Meetings with Sayers Village Society Twineham, Hurst PC and WILD 2pm 26th March
Meeting with Reside tba
Next Liaison Group Meeting 2pm 24th March
Inspectors review of Draft Plan on-going
Speedwatch Scheme | 2025-11-01 | IS | Three sessions planned during Feb/March
Watershed actions to be determined | 2023-01-01 | IM/SA | Riperian Owners Kits available . To be printed and sent to landowners
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known?
Re-Wilding | 2025-11-01 | IS | Post to be removed. Bulbs planted in MG. Plug wildflower plants to be planted in Spring
Silent Soldiers moved to wildflower site.
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba.
APC Website Update | 2024-06-01 | IM | Vision ICT recommendations to be considered and developed by Iain.
B2118 pathway towards Muddleswood | 2024-07-01 | JP | MSDC to clear pathway overgrowth/siding work. Work carried out by WSCC
Allotments Water Supply | 2024-09-01 | SS/SA | Water Butt to be repainted (Spring). Guttering needs repair.
Peter Holding has offered to undertake.
B2116 Lay By and Gully | 2024-11-01 | JP/IM | Clearance of leaves etc reported to MSDC Street Cleaning. Gully cleared but filling again.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Joy Dennis advises that Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
Copper in a Café | 2025-02-01 | ? | Arrange?
Allotment Rubbish | 2025-03-01 | JP/IM/SA | AD Rowe to clear in Spring 26. "No Dumping" sign required.
Trees | 2025-09-01 | SS /IM | Park Linden tree to be trimmed.
Dropped gully by school | 2025-11-01 | ? | Repaired but starting to drop again. Reported to WSCC Highways.
Rec Area Bird Box | 2026-02-01 | JP/IM | fallen box collected by Glendale
SID data | 2026-01-01 | JD | Dave Robson has offered to undertake
Playground | 2026-02-01 | JP/IM | Aditional "No Dogs Allowed" signs required. Glendale are dealing
The Street Mud/Blocked Gullies | 2026-02-01 | JP/IM | Blocked throughout village. Reported.
Twinham Lane Finger Post | 2026-01-01 | IM | Beyond economic repair so to be replaced
Footpath near Yew Tree Cottage | 2026-02-01 | JP/IM | Concrete post required to prevent traffic?
Road Works Signs | 2026-02-01 | JP | Dumped on Albourne Road - to be removed