## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Alison Bennett MP has asked for sight of relevant correspondence
Flashing School warning lights tio be considered
Re-routing of School Bus | 2023-04-01 | JD/IM | Germma Wallis to investigate options with WSCC School Transport Scheme staff
School to be encouraged to produce an Active Travel Plan
Meeting to be arranged between Parish Councillors and School re;presentatives
Sayers Village Proposals | Nov | JS | Second Engagement Meeting with MSDC Liaison Group 24th Nov
Meeting with Welbeck 30th Oct
Meeting with Sayers Village Society and Hurst PC 4th Nov
Sayers Village Workshop 10th Nov
Meeting with Reside tba
Speedwatch Scheme | 2023-01-01 | IS
Watershed actions to be determined | 2023-01-01 | SA | Riperian Owners Kits available . To be sent to landowners
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known.
Re-Wilding | 2024-02-01 | SS/JP/SA | MSDC have withdrawn the site. Millenium Garden site to be seeded by PC
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba
APC Website Update | 2024-06-01 | IM | Vision ICT recommendations to be considered and developed by Iain
The Street/Barleycroft hedge | 2024-09-01 | IM | Trimming to be deferred until end of nesting season. Clarion to undertake.
B2118 pathway | 2024-07-01 | JP | MSDC to clear overgrowth/siding work to be reported to Tim Boxall
Allotments Water Supply | 2024-09-01 | SS/SA | Installing waterpipe too expensive. Water Butt to be provided
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance of leaves etc reported to MSDC Street Cleaning Team. Gully cleared.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Joy Dennis advises that Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - east side | 2025-02-01 | IS/IM | GW Shelter option chosen. Section 106 funds likely to be available
WSCC Bus Services Improvement Fund may also provide finance. Joy D to advise
Copper in a Café | 2025-02-01 | ? | Arrange?
Allotment Rubbish | 2025-03-01 | JP/IM/SA | Clarion to provide quotation for clearing. "No Dumping" sign required.
Millenium Garden and Pound | 2025-04-01 | JP | Pound clearamce unsatisfactory - Brian to carry out in future.
Millenium Hedge trimming to be carried out end Oct
Annual Grit Bin Audit | 2025-06-01 | IM/SA/JP | Bins to be checked for repairs and grit
Singing Hills Collapsed Sign | 2025-09-01 | JP/IM | Tim Boxall will contact Singing Hills
Street Road Signs | 2025-09-01 | SS | MSDC refuse to replace faded signs
Trees | 2025-09-01 | SS /IM | Park Leylandi and Linden adjacent to the footpath to be trimmed.
Landowner advised advised
B2118 Replaced Road Sign | 2025-10-01 | JP | Soil and waste material left by contractor. Tim Boxall handling