## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Alison Bennett MP has asked for sight of relevant correspondence
Flashing School warning lights to be considered
Re-routing of School Bus | 2023-04-01 | JD/IM | Gemma Wallis to investigate options with WSCC School Transport Scheme staff
School to be encouraged to produce an Active Travel Plan
Meeting to be arranged between Parish Councillors and School representatives
Sayers Village Proposals | Nov | JS | Second Engagement Meeting with MSDC Planning tba
Meeting with Welbeck to be arranged
Meeting with Sayers Village Society and Hurst PC tba
Speedwatch Scheme | 2023-01-01 | IS | Truslers Hill Lane to be Scheduled. Six speeders recorded on B2118 (N&S)
Watershed actions to be determined | 2023-01-01 | SA | Riparian Owners Kits available?
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known.
Re-Wilding | 2024-02-01 | SS/JP/SA | Wildflower seeds to be planted Spring 2025. Grass cutting by SA after daffodils.
MSDC have withdrawn the site
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba
APC Website Update | 2024-06-01 | IM | Vision ICT recommendations to be considered
The Street/Barleycroft hedge | 2024-09-01 | IM | Trimming to be deferred until end of nesting season. Clarion to undertake.
B2118 pathway | 2024-07-01 | JP | Pavement needs attention. MSDC to clear overgrowth/WSCC to do Siding if needed
Allotments Water Supply | 2024-09-01 | SS/SA | Installing water pipe too expensive. Water Butt to be provided
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance of leaves etc reported to MSDC Street Cleaning Team. Gully cleared.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Joy Dennis advises that Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - east side | 2025-02-01 | IS/IM | Options to be considered. Land ownership is WSCC
WSCC Bus Services Improvement Fund may provide finance. Joy D to advise
Copper in a Café | 2025-02-01 | ? | Arrange?
Allotment Rubbish | 2025-03-01 | JP/IM/SA | Clarion to provide quotation for clearing. "No Dumping" sign required.
Millennium Garden and Pound | 2025-04-01 | JP | Pound clearance unsatisfactory - Brian to carry out in future.
Millennium Hedge trimming required
Hedge Damage | 2025-06-01 | JP | Gap has been fenced
Annual Grit Bin Audit | 2025-06-01 | IM/SA | Bins to be checked for repairs and grit
Singing Hills Collapsed Sign | 2025-09-01 | JP/IM | Responsible?
Street Road Signs | 2025-09-01 | SS | Signs to be checked and replaced as necessary
Trees | 2025-09-01 | SS | Park Leylandi and adjacent to the footpath to be trimmed.