## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO rejection re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Alison Bennett MP has asked for sight of relevant correspondence
Re-routing of School Bus | 2023-04-01 | JD/IM | Germma Wallis to investigate options with WSCC School Transport Scheme staff
School to be encouraged to produce an Active Travel Plan
Meeting to be arranged between Parish Councillors and School re;presentatives
Clean and Repaint Village Gateways | Oct | JD/JP | Gateways cleaned and repainted
Sayers Village Proposals | Nov | JS | Second Engagement Meeting with MSDC Planning tba
Meeting with Welbeck to be arranged
Speedwatch Scheme | 2023-01-01 | IS | Truslers Hill Lane to be Scheduled. Six speeders recorded on B2118 (N&S)
Watershed actions to be determined | 2023-01-01 | SA | Riperian Owners Kits available?
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help to be determined
Start to be deferred until outcome of the District Plan is known.
Re-Wilding | 2024-02-01 | SS/JP/SA | Wildflower seeds to be planted Spring 2025. Grass cutting by SA after daffodils.
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba
APC Website | 2024-06-01 | IM | To be updated. Vision ICT to recommend improvements
Strimmer Purchase | 2024-07-01 | JP/IM | Makita DUR193RT Strimmer to be ordered. Brian will store.
The Street/Barleycroft hedge | 2024-09-01 | IM | Trimming to be deferred until end of nesting season
B2118 pathway | 2024-07-01 | JP | Pavement needs attention. MSDC to clear overgrowth/WSCC to do Siding if needed
Allotments Water Supply | 2024-09-01 | SS/SA | Installing waterpipe too expensive. Water Butt to be provided
B2116 Lay By and Gully | 2024-11-01 | JP | Clearance of leaves etc reported to MSDC Street Cleaning Team. Gully cleared.
B2118 TLs - Two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage rejected by WSCC Highways. Community Highways Scheme?
Joy Dennis advises that Braking Data may help when available
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
Purchase of land necessary?
B2118 Bus Shelter - east side | 2025-02-01 | IS/IM | Consider new build and Installation. Land ownership is WSCC
WSCC Bus Services Improvement Fund may provide finance. Joy D to advise
Copper in a Café | 2025-02-01 | ? | Arrange?
Dog Bin | 2025-03-01 | IM/SA | For disposal. Possible Dog walking site in Hurst could be interested.
Allotment Rubbish | 2025-03-01 | JP/IM/SA | Clarion to provide quotation for clearing. "No Dumping" sign required.
Millenium Garden and Pound | 2025-04-01 | JP | Pound clearamce unsatisfactory - Brian to carry out in future?
Millenium Hedge trimming required
Hedge Damage | 2025-06-01 | JP | Gap has been fenced
Annual Grit Bin Audit | 2025-06-01 | IM/SA | Bins to be checked for repairs and grit