## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking into TRO decision re 20 mph in context of other TRO decisions
and 300 petition signatures in support.
Chris Stark, WSCC Road Safety Manager, has indicated his support
Gemma Wallis, Highways Manager, to liase with Joy Dennis and Chris Stark
Meeting with Gemma Wallis | 2025-01-01 | JD | Meeting arranged for 9.00am 13th March to progress outstanding Highways issues
Re-routing of School Bus | 2023-04-01 | JD/IM | Germma Wallis to investigate options with WSCC School Transport Scheme staff
Shaves Wood Lane Speeding traffic | 2022-11-01 | JD | TRO for change to 40 mph approved by WSCC Highways and implemented
Clean and Repaint Village Gateways | Oct | JD/JP | Gateways cleaned and veg cleared. De-rusting and painting of bolts to be scheduled..
Sayers Village Proposals | Nov | JS | Mtg with A Simpson and D Turner of Welbeck Land for 20th March cancelled
Speedwatch Scheme | 2023-01-01 | IS | B2116 residents needed to join team. Next event tba during better daylight
Watershed actions to be determined | 2023-01-01 | SA | Work Completed ?
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help and timing to be determined
Re- Wilding | 2024-02-01 | SS/JP | Wildflower seeds to be planted Spring 2025. Grass cutting after daffodils.
Blocked and Dropped Drain by School Gate | 2024-04-01 | SA/SS | Tim Boxall has confirmed that repairing the The Street gully is a listed job
Blocked B2116 drains adjacent to Albourne Court entrance cleared
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated. Next mtg tba in March
APC Website | 2024-06-01 | IM | To be updated. Vision ICT to recommend improvements
Strimmer Purchase | 2024-07-01 | JP | Choice to be reviewed with Brian Spring 2025
Playground Gate Springs x3 | 2024-07-01 | JP | All replaced
The Street/Barleycroft hedge | 2024-09-01 | IM | Needs trimming. APC Emails to Clarion to be forwarded to Tim Boxall
B2118 pathways blocked | 2024-07-01 | JP | Pavement needs attention. Reported to Andy Tuck
Allotments Water Supply | 2024-09-01 | SS | Installing waterpipe too expensive. Alternatives to be considered
B2116 Lay By | 2024-11-01 | JP | Need for fallen leaves and mud to be reported to MSDC Street Cleaning Team
B2118 TLs - two lanes into one safety issue | 2025-01-01 | JD/JP | Additional signage frejected by WSCC Highways. Community Highways Scheme?
Church Lane - hedges overgrowing road | 2025-01-01 | JP | All hedges cleared except for Ragged Dog . Tim Boxall has contacted owner
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected
B2118 Bus shelter -west side | 2025-02-01 | ? | Peter Holding has offered to maintain. APC to supply materials
B2118 Bus Shelter - east side | 2025-02-01 | IS | Consider new build and Installation. Land ownership is WSCC
Albourne Road Hedge - south side by TLs | 2025-02-01 | JP | Trimmed
Copper in a Café | 2025-02-01 | ? | Arrange?
Dog Bin | 2025-03-01 | IM | For disposal