## Sheet1
ISSUE | DATE | LEAD | STATUS
B2116 TRO For Speed Limit changes | 2022-03-01 | JD | Joy Dennis looking intoTRO decision re 20 mph in context of otherTRO decisions
Chris Stark, WSCC Road Safety Manager, has advised on alternative measures
Andy Tuck to raise work order for 40 mph where national Limit applies. Jan start.
APC to organise petition of local residents and businesses for 20 mph request
Pavement from B2118 TLs to A23 Boundary | 2024-12-01 | JP | Pavement needs clearing of overgrowth
Meeting with Adam Denby | 2025-01-01 | JD | To be arranged in February to progress outstanding Highways issues
Re-routing of School Bus | 2023-04-01 | JD/IM | Adam Denby to investigate options with School Transport staff
Shaves Wood Lane Speeding traffic | 2022-11-01 | JD | TRO for change to 40 mph approved by Highways
Clean and Repaint Village Gateways | Oct | JD/JP | Gateways cleaned and veg cleared. De-rusting and painting of bolts to be scheduled.
Sayers Village Proposals | Nov | JS | Adrew Simpson consultancy proposal accepted
Speedwatch Scheme | 2023-01-01 | IS | B2116 residents needed to join team. 9 letters issued following B2118 speedwatch
Watershed actions to be determined | 2023-01-01 | SA | Work Completed ?
Neighbourhood Plan | 2023-08-01 | JS | Project Team to be formed. Need for professional help and timing to be determined
Councillor Email Addresses | 2023-10-01 | IM | Vision Express email proposal implemented
Winter Maintenance Plan | 2023-11-01 | SA | Barleycroft salt bin to be refilled during Autumn 2025
Re- Wilding | 2024-02-01 | JP | Wildflower seeds to be planted Spring 2025
Blocked and Dropped Drain by School Gate | 2024-04-01 | SA/SS | Adam Denby to arrange for Drainage Team to inspect and repair The Street gully
Adam Denby to check clearance of B2116 drains adjacent to Albourne Court entrance
Rec Ground Trees | 2024-05-01 | SS | E Nelson /Glendale to attend and inspect to be followed up
Drainage meeting with S White (Sayers Common) | 2024-04-01 | SA/JS/JD | Action Notes to be circulated.
APC Website | 2024-06-01 | IM? | To be updated. Vision ICT to recommend improvements
Strimmer Purchase | 2024-07-01 | JP | Choice to be reviewed with Brian Spring 2025
Playground Gate Springs x3 | 2024-07-01 | JP | Need replacing. Reported to Elizabeth Nelson.
The Street/Barleycroft hedge | 2024-09-01 | IM | Needs trimming. To be reported to Clarion
B2118 pathways blocked | 2024-07-01 | JP | Overgrowth between South View Grange and The Chase cut back.
Pavement needs attention. Reported to Andy Tuck
Allotments Water Supply | 2024-09-01 | SS | Possibility of installing waterpipe to be considered
B2116 Lay By | 2024-11-01 | JP | Need for fallen leaves and mud to be reported to MSDC Street Cleaning Team
B2118 TLs - two lanes into one safety issue | 2025-01-01 | JD/JP | road arrows are inadequate. Andy Tuck to reconsider slip road proposal
Church Lane - hedges overgrowing road | 2025-01-01 | JP | Tim Boxall to write to landowners
B2116 Pavement between The street and the lay by | 2025-01-01 | JD | Historical approval to improve road/pavement differentiation to be resurrected